## Sheet1
Timeline					Date Due	Completed

		Austin	Bryan	Dylan	Taylor

Atmega
temp					X	02/19/16
precip				X		02/15/16	02/15/16
rtc					X	02/19/16
sms					X	02/19/16
flow			X			02/15/16	02/15/16
actuator			X			02/19/16	02/15/16
communication to BL600			X
algorithm			X			02/29/16
flash from UART

Android
transmit sqrft		X		X		03/31/16
transmit date		X		X		03/31/16
transmit lattitude		X		X		03/31/16
pull sensor data					03/31/16

BL600
communication to Atmega		X
communication to Android app		X

Power
battery system					X	03/01/16
main power				X		03/01/16

Enclosure
waterproof build					X	03/01/16

Design Documentation
initial schematic				X		2/26/2016
ongoing schematic review		X	X	X	X	03/15/16

	LB	6	5	7	6